## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
Story 1: Project setup and base application structure | 2 | 2025-12-03 | Initialized the Vue 3 project, set up the base application structure, created Header and Footer components, implemented Home and About views, configured Vue Router, and applied initial styling.
Story 2: House Listing component | 3 | 2025-12-04 | Created House Listing component, and added global and House Listing styles.
Story 2: State management setup (Pinia) | 1 | 2025-12-05 | Integrated Pinia for state management and configured the initial global store.
Stories 3 and 4: Store optimization: sorting, filtering, search | 1 | 2025-12-05 | Optimized the Pinia store by adding sorting, filtering, and search logic.
Stories 3 and 4: Search and header UI implementation | 2 | 2025-12-10 | Implemented HTML and CSS for sorting, filtering, search logic, and header layout.
Story 5: House Details view | 2 | 2025-12-13 | Created the House Details view, added responsive styling, implemented house posting in the store, and conditionally rendered action buttons based on ownership.
Bug fixing and development environment cleanup | 1 | 2025-12-15 | Resolved multiple development and linting errors, including setup configuration issues, WebSocket connection problems, and Vue component naming conventions.
API data handling fix (house details) | 1 | 2025-12-15 | Fixed a network error related to fetching house details by correcting the Pinia getHouseById logic to properly return a single object instead of an array.
Story 5: House Details view styling | 1 | 2025-12-15 | Added styling and layout of the House Details view.
Story 5: House Details view styling | 1 | 2025-12-18 | Improved styling and layout of the House Details view.
Story 5: Delete and Edit buttons. Story 8: Edit view | 1 | 2025-12-22 | Styled edit and delete buttons on the Details view, and created the Edit view.
Story 9: Delete functionality and Modal component | 1 | 2025-12-23 | Implemented deleting functionality in the store, created and styled the Modal component with a warning.
Story 6: House creation implementation | 1 | 2025-12-24 | Implemented the house creation logic, including form logic, image upload, and API integration.
Story 6: Create view styling | 1 | 2025-12-26 | Added styling of the Create view.
Story 8: House editing implementation | 3 | 2025-12-29 | Implemented the house editing logic, including form logic, image upload, and API integration.
Global styling and UI polish | 1.5 | 2025-12-30 | Added overall styling to the House Listing component, and Create, Edit, and Details views.
Story 7: Delete and Edit buttons. Story 3: No results message | 1 | 2025-12-30 | Added edit and delete buttons to the Home view, and implemented a styled "no results" message for empty search results.
Stories 6 and 8: Form validation (Create & Edit views) | 3 | 2026-01-03 | Implemented and styled custom form validations for the Create and Edit views using Vuelidate.
Bonus task: recommemded houses | 1 | 2026-01-05 | Implemented recommended houses logic to the Details view based on price similarity. Added layout and styling. | x
Bonus task: About view | 1 | 2026-01-05 | Implemented and styled the About view. | x
Typography and final UI improvements | 2 | 2026-01-05 | Improved typography and applied final styling.
Total amount of hours | 29.5